## Sheet1
PROJECT NAME PROJECT NUMBER
COMMISSIONING PLAN CHECKLIST
REVISION - DATE
Installation company name:
Address: Phone number:
Contact name: Phone number:
Task / Stage |  | Person responsible | Signature | Tick
Pre-construction phase:
Appoint commissioning manager (CM) or assign specific responsibilities for commissioning process
Distribute design to main contractor (MC), designers (D), installers, commissioning engineer(s), facilities manager(s)
check design(s) for commissionability
check design for ease of maintenance
Make design changes if identified above
Agree communication pathway
Produce commissioning method statement (CMS) for each system COMMISSIONING PLAN
Produce commissioning timetable (plan) with critical path analysis
Co-ordinate commissioning timetable with other services - determine strategic mechanical and electrical co-ordination points - approve timetable
Construction phase/pre-handover:
Have there been any equipment substitutions from original design? Tick if yes.
If yes above, does substitute equipment meet the design requirements? Tick if yes.
Has designer been consulted on any proposed location changes of items to suit site constraints? Tick if yes.
Install and wire hardware as per design and/or instructions and certify completion
During construction phase review commissioning timetable in light of process
Perform pre-commissioning check from CMS and provide written confirmation of fitness for commissioning
Schedule, perform and certify off-site commissioning checks from CMS
Perform commissioning as per CMS
Witness commissioning checks as per CMS
Certify commissioning completion
Complete 'as installed drawings for instruction for O&M manual
Train facilities manager, maintenance staff and/or end users in system operation as per CMS
Draw attention to maintenance risk assessments required and access equipment necessary
Sign completion certificate
Post-handover phase:
Schedule and complete post-handover checks (e.g. seasonal operations) if required by CMS
Complete end user trining as required by CMS
Installer:
Witnessed by: |  | Position: Designer
Company: | Date:
Witnessed by: |  | Position: Commissioning engineer
Company: | Date:
NOTES: